## Sheet1
Task | Assigned to | Progress | Start | End | Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Analysis |  |  |  |  | Proposal
Proposal | Cody, Kaito | 100% | 2025-07-24 | 2025-07-28 | Create and distribute survery
Create and distribute survery | Kaito | 100% | 2025-07-29 | 2025-07-31 | Identify FR, NFR and Constraints
Identify FR, NFR and Constraints | Cody, Kaito |  |  |  | Determine Scope
Determine Scope | Cody, Kaito |  |  |  | Generate alternate designs
Design |  |  |  |  | Write evaluation critea
Generate alternate designs | Cody |  |  |  | Select Preferred Design
Write evaluation critea | Kaito |  |  |  | Create preferred design
Select Preferred Design | Cody, Kaito |  |  |  | Identify ethical and legal issues
Create preferred design | Cody, Kaito |  |  |  | Research object detection
Identify ethical and legal issues | Kaito |  |  |  | Research image processing
Develop |  |  |  |  | Data collection and labelling
Research object detection | Cody |  |  |  | Train the model
Research image processing | Kaito |  |  |  | Test the model
Data collection and labelling | Kaito |  |  |  | Develop the project
Train the model | Cody |  |  |  | Test the project
Test the model | Cody |  |  |  | Collect data
Develop the project | Cody |  |  |  | Evaluate the solution
Test the project | Cody and Kaito
Evaluation
Collect data
Evaluate the solution